## Sheet1
Date | Times | Attendees | Notes | Sprints Agreed
2023-03-01 | 11:00am - 12:30pm |  | •Meeting with Product Owner •Created GitHub Repository •Quick Backlog | •Flowcharts to be created for each requirement
2023-03-06 | 15:00pm - 16:30pm |  | •Flowcharts handed in •Plans for next meeting | •Trello to be setup
2023-03-08 | 11:00am - 12:30pm |  | •Trello has been set up and everyone has been added •Flowcharts updated to trello •Requirements & backlog added to trello | •Create a draft for the design of the webapp
2023-03-13 | 15:00pm - 16:30pm |  | •Designs showcased for layout of the webpage. | •Login - front end - for Wednesday - Pages All Upto Date - Extra Features for Site.
2023-03-15 | 12:00pm - 13:30pm |  | Search bar added - login frontend-going well - pages on website created | •Create and deploy the database for 29th March
2023-03-20 | 11:00am - 13:00pm |  | Database created | Do backend for login
2023-03-29 | 12:00pm - 13:30pm |  | Database was to be done by today, unfortunately couldn't get onto the one made so had to remake it. | backend done for login,register and logout for 3rd April
2023-04-17 | 11:30am - 12:20pm |  | Spoke about what needed to be done next and what has been completed over holiday | Data from excel to be added into the database
2023-04-19 | 15:00pm - 15:30pm |  | Data was added into the databse and spoke about needing to allow the user to add data | Adding data from user was the next step
2023-04-24 | 13:45 - 15:00 |  | Asking if the data can be inputted into database | To start presentation and get the mediocre tasks sorted
2023-05-02 | 11:00-11:30am |  | Data still not been added to database. Main priority | Get the presentation finished and get the data added into the database
2023-05-03 | 11:00am - 13:00pm |  | Still no data added to database - Presentation Finished | Everyone to work on the add data
2023-05-08 | 12:00pm - 12:30pm |  | Data added to the database | To add validation and a few more fields to the add data page
Asa
Mohammad
Jack
Asa
Mohammad
Jack
Asa
Mohammad
Jack
Asa
Mohammad
Jack
Asa
Mohammad
Jack
Asa
Mohammad
Jack
Asa
Mohammad
Jack
Asa
Mohammad
Jack
Asa
Mohammad
Jack
Asa
Mohammad
Jack
Asa
Mohammad
Jack
Asa
Mohammad
Jack
Asa
Mohammad
Jack